Spoiler
- Traditional planning techniques
  - rely on structured and well defined processes
  - work best in predictable environments
- Software is not always developed in a predictable environment
- Agile techniques try to overcome the limitations of traditional planning

---
Traditional
Planning and Scheduling

---
Planning
- The process of deciding what activities have to be performed in a project
- In software development you can define activities starting from the many different processes there are: waterfall, spiral, incremental, RUP, ...
- Representations:
  - Work Breakdown Structures
  - Gantt Charts
  - Activity diagrams

---
The Gantt Chart
- A visual representation of the schedule of a project
- Task/Activity: a represenation of the work to be performed
- Deliverable: a concrete and measurable output of the project
- Milestone: an important date of the project

---
Example of Gantt Chart
Source: Clark, Wallace and Gantt, Henry, “The Gantt chart, a working tool of management”, The Ronald Press Company, New York, 1923 (available in digital format from various sources on the Internet)

---
A modern example

---
A modern example: Resource Usage

---
Scheduling
- Effort (or work): the time an activity takes to be completed
- Manpower: the effort that can be produced in a unit of (calendar) time
  - Can be made of number of units and availability
- Duration: how long an activity will last

---
Scheduling
- Fix any of the two and you can compute the third
- Fix one, variate the second and the third derives from the equation
- Estimations are usually effort-driven
- The formula is a simplification holding in certain reasonable ranges
D = {E} over {M}

---
The (Software) Estimation Process
Specification
of work
“Magic” Box
Effort
Scheduling
Equation
D, E, and M
Specification of work
  - Software requirements
“Magic” Box
  - Experience
  - Analogy
  - Brainstorming
  - Delphi
  - Algorithms (function points/COCOMO)

---
Weaknesses
- The “chicken and egg” problem: no plan without requirements; no requirements without a plan (and a contract)
- Software development and software maintenance are planned in a rather different way, although they are not so diverse in nature
- The accuracy of your plans depends on the accuracy with which you estimate the effort. Reliable effort estimations are difficult